## Sheet1
Task | Notes | Suggested assignment | Status | Priority | Required for v1?
There is an API parameter that I need to add to a Client API call (updateState). Currently I'm figuring out which actions to display in the UI by parsing the Action Request - but this should be converted to a series of Boolean values | May not make sense. Need further refinement of the idea | Kevin |  | Medium | No
We need to verify all Use Cases | Original Use Cases are 1. Test Automation 2. Security Camera | Michael | Partiially complete | High | Yes
We need to verify that all "Test" references (outside of the Demos) are gone | Cleanup | Kevin | Complete except for new code changes | High | Yes
We need to verify that Filters work as intended | Functionality will likely change with new UI | JD/Kevin |  | High | No
We need to verify that the File Storage Service works as intended | Validation | Kevin | Partially complete | High | Yes
We should setup a demo Power BI Dashboard as a sample Use Case (using the demos as the data) | Save as Power BI Desktop file and provide link in index.html | Michael |  | Medium | No
We should add Authentication | Functionality is dependent on UI | JD/Kevin |  | Medium | No
I suspect that the Health Service is not quite functioning correctly, so some verification is required | Validation, but may not have env to verify all of Health Service | Kevin | Completed | High | Yes
We need to flesh out and organize all of the documentation | In good shape | Kevin | Complete except for new code changes | High | Yes
We need to verify multi-user support | Validation | Michael/Kevin |  | High | Yes
We need to verify that large numbers of Custom Actions have no negative effects (both on performance and the UI) | Validation | Kevin |  | Medium | No
We need to verify that larger numbers of Runs have no negative effects (again on both performance and the UI) | Validation | All |  | High | Yes
We need to include steps of replacing configuration values with dummy values | Cleanup | Kevin |  | High | Yes
We should consider rebuilding/refining the UI | Redesign, but also to protect uniqueness | JD |  | Medium | No
We should add Diagrams | Doc | All | Started | High | Yes
We should define up-to 10 Use Cases | Doc | Michael./JD |  | Medium | No
We should create a self-sufficient Docker Container (for all Services) | Simplify install process for Demo | JD |  | Medium | No
We should create a JS Client reference library | Post v1, but need to flesh out Client support | Kevin |  | Medium | No
We should add a Performance and Security Doc | Doc | Kevin | Complete except for new code changes | High | Yes
We should add support for REST API calls | Missing functionality | Kevin |  | Medium | No
We need to add Unit Tests | Missing functionality | Michael/Kevin |  | Medium | No
We need to define the code merge process |  | All
We may want to remove the autorefresh button (especially if a new UI is being deployed) |  | JD/Kevin
Remove Compilation Warnings | As many as we can | Kevin
Add a cleanup column to the Execution UI | In case a failure occurs that wasn't caught by automation | Kevin | Completed
Verify Scheduler functionality works |  | Kevin | Completed